Simplifi Med Ltd

PROJECT CHARTER

Cardiology AI: Reading ECGs and Echo Studies

Decision support prototype for Simplifi Med Ltd

Client and sponsor

Simplifi Med Ltd, Dr Alaa

Module

COS6032-E Industrial AI Project, University of Bradford

Module leader

Dr Kulvinder Panesar

Group number

B26

Project management

CDIO with Scrum, tracked in Jira (project CAI)

Team member

Role

Student number

Alaedine Ait Bella

Project manager and technical lead

24019746

Reyad Taha

Data analyst

24005092

Pana Sharif

Tester, code refiner, ethics and legal

22011714

Version

Date

Status

Prepared by

1.0

19 October 2026

Submitted for approval

Alaedine Ait Bella

1. General project information

Project name

Cardiology AI: reading ECGs and echo studies

Project ID

CAI (Jira)

Project manager

Alaedine Ait Bella

Project sponsor

Dr Alaa, Simplifi Med Ltd

Organisation unit

University of Bradford, COS6032-E

Supervisor

Dr Kulvinder Panesar

Expected start

19 October 2026

Expected completion

26 April 2027

Estimated cash cost

About £75 (cap £100)

Team effort

About 600 hours

Methodology

CDIO phases with two-week Scrum sprints (12 sprints)

Document status

Draft for approval

2. Project overview

Problem or issue

ECGs and echo studies are read under time pressure, often by junior clinicians out of hours with no cardiologist nearby. Reading quality depends on who reads the study, and existing AI tools, mostly from the United States, are expensive (Simplifi Med Ltd, 2026).

Purpose of project

To build and test a prototype that says whether an ECG or echo study looks normal or abnormal, how confident it is, what it looked at, and who to contact, using a fixed table signed off by a clinician. A clinician confirms every result. It is a second opinion, not a diagnosis.

Business case

A simple, explainable tool can make escalation of acute changes faster and more consistent at low cost. We considered three options: do nothing (reads stay inconsistent), buy an imported tool (expensive and opaque), or build a simple prototype. We recommend building, because it is low cost, transparent and fits the client’s fixed escalation table.

Goal (SMART)

By 16 April 2027, build, test and demonstrate a decision support prototype that classifies ECGs and echo studies with calibrated confidence, an explanation and a fixed-table action, meets the client-confirmed targets on public practice data, and is shown at the AI Exhibition on 19 or 20 April 2027.

Expected deliverables

Research summary and baseline results; trained models with code and settings; comparison of at least three approaches per study type; the findings-to-action table; a working app with audit log and user guide; governance strategy, FAIR report, final report and client summary; poster and live demo.

3. Objectives and key results

#

Objective

Key results (target date)

Owner

O1

Deliver a trustworthy ECG classifier

1. At least 90% of abnormal ECGs flagged, with no more than 20% false alarms (28 Feb 2027)

2. At least 95% of acute changes flagged (14 Mar 2027)

3. Three or more approaches compared on one protocol, with calibration reported (28 Feb 2027)

Alaedine, Pana Sharif

O2

Deliver a safe, auditable app with an echo pathway

1. Three or more echo approaches compared and echo target agreed with the client (14 Mar 2027)

2. Every run shows finding, confidence, explanation and action, and is logged (28 Mar 2027)

3. Suggested action agrees with clinical review in 18 of 20 cases (9 Apr 2027)

Reyad, Pana

O3

Run the project professionally and responsibly

1. Repo shared in week 1 and every blog entry within 3 weeks (ongoing)

2. All project rounds attended, with a client meeting after each (ongoing)

3. Governance strategy and FAIR log complete (16 Apr 2027)

All

Key results are scored from 0 to 1 at every project round in the OKR scorecard (Doerr, 2018).

4. Success criteria

Measure

Target

How it is measured

Abnormal ECGs flagged (sensitivity)

9 in 10 or more

Held-out PTB-XL test fold

Acute changes flagged

19 in 20 or more

Agreed acute-change labels

False alarms on normal ECGs

2 in 10 or fewer

Held-out PTB-XL test fold

Echo performance

Set with the client after first results

EchoNet-Dynamic fixed test group

Honest confidence

Stated confidence matches observed accuracy

Calibration error and reliability plot

Right next step

18 of 20 cases agree

Cardiologist or clinical lead review

Repeatable

Same results from a fresh copy

Rerun by another team member

Targets are the client’s suggestions and will be confirmed at the first client meeting (Simplifi Med Ltd, 2026).

5. Project scope

Within scope

Reading 12-lead ECGs; reading echo pictures and clips; normal or abnormal with confidence; spotting acute changes; showing what the model looked at; recommending who to contact from a fixed table; an audit log; a working app and written report.

Outside of scope

CT and MRI; anything shown to patients; treatment, drug or dose advice; free text written by a model; links to hospital systems; medical device approval; use on real patients during the project.

Change control

Any change to scope needs written agreement from the client and the module organiser, and is logged in Jira and on the group blog.

6. Tentative schedule

Key milestone or phase

Start

Finish

Initiate: repo shared, blogs, NDA, charter, PID, Jira (Sprint 1)

19 Oct 2026

1 Nov 2026

Conceive: data understanding, kick-off meeting, ECG baseline (Sprints 2 to 3)

2 Nov 2026

29 Nov 2026

Design: experiment design, architecture, action table draft (Sprints 4 to 5)

30 Nov 2026

3 Jan 2027

Element 1 individual reports submitted

4 Jan 2027

4 Jan 2027

Implement: ECG and echo models, app, rule engine, audit log (Sprints 6 to 10)

4 Jan 2027

14 Mar 2027

Operate: end-to-end testing, user guide, client review (Sprint 11)

15 Mar 2027

28 Mar 2027

Close: poster, demo, governance and evidence upload (Sprint 12)

29 Mar 2027

16 Apr 2027

AI Exhibition: poster and live demo

19 Apr 2027

20 Apr 2027

Element 2 reports and project closure

26 Apr 2027

26 Apr 2027

Project rounds take place every 2 to 3 weeks; each sprint review is held just before a round. Dates are copied from Canvas when published.

7. Resources

Project team

Alaedine Ait Bella (project manager, technical lead); Reyad Taha (data analyst); Pana Sharif (tester, code refiner, ethics and legal). The ScrumMaster role rotates every sprint.

Support resources

Dr Alaa and the client’s clinical lead ; Dr Kulvinder Panesar and the module team at project rounds.

Data

PTB-XL (about 21,800 ECGs) and EchoNet-Dynamic (over 10,000 echo videos) until written trust approval for client data.

Tools

GitHub, Jira, group and individual blogs, Python, PyTorch, FastAPI, free-tier and university GPU time.

Special needs

Signed NDA before confidential material; written trust approval before any real patient data.

8. Stakeholders

Name

Title

Role and responsibility

Interest / influence

Dr Alaa

Client, Simplifi Med Ltd

Sets targets, signs off the action table, reviews increments

High / High

Dr Alaa                 [to be approved ]

Client clinical lead

Owns the action table, checks labels and wording

High / High

Dr Kulvinder Panesar

Module leader

Runs project rounds and assessment

High / High

Alaedine Ait Bella

Project manager

Plan, Jira, client liaison, system design, echo, app

High / High

Reyad Taha

Data analyst

Data preparation, splits, ECG experiments

High / Medium

Pana Sharif

Tester, ethics and legal

Testing, calibration, governance, FAIR log

High / Medium

Pilot trusts and clinicians

Future users

Approve data use; give feedback on usefulness

Medium / High

9. Costs

Cost type

Item

Rate

Quantity

Amount

Labour (notional)

Team effort, 3 students

£15 per hour

600 hours

£9,000

Compute

Cloud GPU, only if free tiers are not enough

Pay as used

As needed

£40

Supplies

A1 poster print for the exhibition

£25

1

£25

Software

GitHub, Jira free plan, Python libraries, open data

£0

n/a

£0

Contingency

About 10% of cash costs

n/a

n/a

£10

Total cash cost

£9075

Labour is notional and is not paid; it shows the value of team time. Bottom-up estimate based on about 10 hours per person per week over 20 active weeks.

10. Benefits

Type of benefit

Description

Basis of estimate

Faster escalation

Acute changes flagged with a clear next step

Client brief; tested against acute labels

Consistency

The same evidence and rule shown for every study

Fixed action table and audit log

Lower cost

Simpler than expensive imported tools

Client brief

Trust and safety

Confidence and evidence always shown; clinician decides

Governance strategy

Reuse

Documented code and method for the pilot trusts

GitHub repository and user guide

11. Risks, constraints and assumptions

ID

Key risk

Score

Response

Owner

R3

Data leakage: studies from one patient appear in both training and test sets

15

Patient-level splits; Pana reviews the split code.

Reyad, Pana

R1

Trust data approval is slow or refused (client brief)

12

Start on public data; no real data before written approval.

Alaedine, Dr Alaa

R4

Too few abnormal studies, class imbalance

12

Balance classes; report misses, not just accuracy.

Reyad

R8

Scope creep into CT, MRI or treatment advice

12

Scope baseline and written change control.

Alaedine

R9

Claims go beyond what the results support

12

Report limits; clinical lead reviews wording.

All

Score is likelihood multiplied by impact, each rated 1 to 5. The full register of 17 risks is in the PID.

Constraints

Fixed assessment dates; three part-time team members; decision support only, with no live patients; approved storage only; free-tier and university compute.

Assumptions

Public data is used until written trust approval; the client confirms the suggested targets; the acute-change label is agreed in Sprint 4; the NDA is signed before confidential material is shared.

12. Approval

Role

Name

Decision

Signature

Date

Client and sponsor

Dr Alaa

Module leader

Dr Kulvinder Panesar

Project manager

Alaedine Ait Bella

Data analyst

Reyad Taha

Tester, ethics and legal

Pana Sharif

Prepared by

Alaedine Ait Bella

Date

19 October 2026

References

Doerr, J. (2018) Measure what matters. New York: Portfolio/Penguin.

Panesar, K. (2026) COS6032-E Industrial AI Project: assignment brief and assessment information. University of Bradford.

Schwaber, K. and Sutherland, J. (2020) The Scrum Guide. Available at: https://scrumguides.org (Accessed: 19 October 2026).

Simplifi Med Ltd (2026) Cardiology AI: reading ECGs and echo studies. Client brief, September 2026.